## May-14-2015
Date: |  | 14/5/2015
Subject |  | Discuss about choosing project and giving task for next week
Notes taken by: |  | ThienVH
Present: |  | Mr. TriTD and project team (HoangTV, ThienVH, ThanhTC, TaiHD, ThienNN, ThaiPQ )
Apologies: |  | None
No | Notes taken |  | Assign to | Deadline | Comments
1 | - Change subject of the project: + Vietnamese: Hệ thống tìm việc + English: Job searching system - About the new project: + Help people searching job + Help company posting their recruitments. + Match the job with the job-seeker automatically. + Focus on searching. (This is the key function of the system). + Get charge from the company's posting and ads. + Consider about recruitment process. + Make appointment between company and applicant. + Manage job's status. |  | Project Team | 2015-05-14 | - Project team all agreed to work with the new object
2 | Tasks for next week: - Update Report #1 and Report #2 - Learn about the system: + User group + Functions of each group - Complete Report #3 - Have a meeting without present of lecturer and writing minute. |  | Project Team | 2015-05-21 | - Learning form the following website: + http://www.careerlink.vn/ + http://www.jobstreet.vn/ + http://www.vietnamworks.com/ - Discuss about new project: 16-May 08:30 am. (online meeting) - Another meeting of team members will hold every Tuesday 01:00 pm at school.
3 | Project planning: - Complete report #4 before Jun-5. - Complete coding & testing before Jul-15 - Repair and upgrade codeding from Jul-15 til Aug-15. |  | Project Team | N/A