## May-21-2015
Date: |  | 21/5/2015
Subject |  | Review Report #1, Report #2, and Website functions
Notes taken by: |  | ThienNN
Present: |  | Mr. TriTD and project team (HoangTV, ThienVH, ThanhTC, TaiHD, ThienNN, ThaiPQ )
Apologies: |  | None
No | Notes taken |  | Assign to | Deadline | Comments
1 | * Report #1 Review: - Remove Objectve part, keep Purpose and Idea part. - Correct grammar and wrong words. * Report #2 Review: - Existing System: has some disadvantages, try to develop a system which can solve all the problems of the existing product. - Proposed System: + Copy from the Purpose part - Report #1. + Including the features that make the whole system better than the existing systems. - Project plan: missing this part; update and review next week. - Project team: missing organization diagram. * Report #3: - Discuss about: sequence of operation, flow of event. - Show the report #3 next week. * Other comments: - Using Github instead of Google code |  | Project Team | 2015-05-28
2 | Send an email to request change the theme of capstone project.From Anime Vietsub Sharing System into Job Searching System. |  | TaiHD | 2015-05-21 | Done