## May-28-2015
Date: |  | 28/5/2015
Subject |  | Review Report #1, Report #2, Report #3, Discuss how to build the system
Notes taken by: |  | ThienVH
Present: |  | Project team (HoangTV, ThienVH, ThanhTC, TaiHD, ThienNN, ThaiPQ )
Apologies: |  | None
No | Notes taken |  | Assign to | Deadline | Comments
1 | * Report #1: - Change: + chance and challenger. (Purpose part) + similar = just like * Report #2: - Change: + italic and bold project name (Project Name part) + existed = existing (Proposed part) + Iteration = iterative + add missing part of the project plan. * Report #3: + Adding user group before requirement. + Create Manager Account belongs to Manage Account. + Add new user group: Satff. + Staff: manage job, manage topic, manage ads. (but ads cost is decided by manager) |  | Project Team | 2015-06-02 | - Done editing Report #1
2 | Recruiting Process: - Posting Job -> Check in Real -> Mark as Checked -> Job is now accepted. Disscuss about Business Rule: - Guest cannot login. - Login for other role. ERD: - CV and Profile must be clear. - Add Entities Fly or Advertise. - Customer for advertising. - Package Online: make it clearer. --> Service Package and Type - Moderator --> Manager - change "has" into another word. - Missing Category. |  | Project Team | 2015-06-02
3 | Assign task: - Complete Report #1, #2, #3. - Create Report #4: + Architecture Design Diagram + Detailed Design + Graphical User Interface + Sequence Diagram. + Create page for each function. + Class Diagram. + Database Diagram. - Statistic Function: what, how? |  | Project Team | 2015-06-04