## Jun-11-2015
Date: |  | 2015-11-06
Subject |  | Review Report #3, Report #4
Notes taken by: |  | ThienVH
Present: |  | Mr. TriTD and project team (HoangTV, ThienVH, ThanhTC, TaiHD, ThienNN, ThaiPQ )
Apologies: |  | None
No | Notes taken |  | Assign to | Deadline | Comments
1 | Review Report #3: - Manage Applied Job: do not need to change. - Manage Skill: change into Manage Own Skill. - Change order of the list functions. - Remove word "Requirement" from heading. - Remove function Manage Resume. Function Manage Profile is now used for CV management. - Manage Benefit: change another word. - Find Job Seeker CV: not good. - Buy Job Package: discuss later with team. - Staff: +Process Job Package Request. - Package: number of jobs, day expired. - Manage Jobs: Add Job ....--> Found Job Seeker (The whole process and Matching function). |  | Project Team | 2015-06-13 | - Send by mail
2 | Review Report #4: - 4.3: Redo - Write component diagram. |  | Project Team | 2015-06-18