## Jun-18-2015
Date: |  | 18/6/2015
Subject |  | Review Report #4, Report #3
Notes taken by: |  | ThienVH
Present: |  | Mr. TriTD and project team (HoangTV, ThienVH, ThanhTC, TaiHD, ThienNN, ThaiPQ )
Apologies: |  | None
No | Notes taken |  | Assign to | Deadline | Comments
1 | * Review Report 4: - Design Overview: put description part above the image. - Component diagram: Change position of View Module and Controller Module; name the component (SearchModel, SearchView, SearchController, Apply, …) - CRC: must complete. * Review Report 3: - Get job alert function: have a link on any email: "Tôi không muốn nhân email từ web này nữa"; check duplicated email and if it is, inform user about the existance; it's not suitable for the website to send all the email for every job (cracks,...); this function can be removed. - All functions are accepted. - Check ERD & database. *GUI: - Check datetime when job expire. - Which algorithms, which data structures. - For both Window and Unix. |  | Project team | 2015-06-19 | - Send mail
2 | - Coding - Built Report 5 - Class diagram - Meeting next week. |  | Project team | 2015-07-02